## Projektplanlægger
Projektplanlægger
| Fremhæv et tidsrum til højre. Derpå følger en forklaring af diagrammet. |  |  |  |  | Fremhævning af tidsrum: | 1 |  |  | Varighed for plan | [6 empty] | Faktisk startdato | [6 empty] | % fuldført |  |  |  |  | Faktisk (ud over plan) | [7 empty] | % fuldført (ud over plan)
CASE | NAVN | STARTDATO FOR PLAN | VARIGHED FOR PLAN | FAKTISK STARTDATO | FAKTISK VARIGHED | PROCENTDEL FULDFØRT | TIDSRUM
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
LOGO | NICKI | 1 | 1 |  |  | 0%
CONTACT | NICKI | 2 | 1 |  |  | 0%
GEN. LAYOUT | NICKI | 4 | 2 |  |  | 0%
NAVIGATION | NICKI | 3 | 1 |  |  | 0%
SLIDER | ASGER | 1 | 2 |  |  | 0%
SOCIALS | HELENA | 1 | 1 |  |  | 0%
FOOTER LINKS | HELENA | 2 | 1 |  |  | 0%
ADDRESS | HELENA | 3 | 1 |  |  | 0%
PAYMENT OPT. | HELENA | 4 | 1 |  |  | 0%
BRANDS | MIKKEL | 1 | 2 |  |  | 0%
CATEGORY | MIKKEL | 3 | 2 |  |  | 0%
SEARCH BAR | ASGER | 3 | 1 |  |  | 0%
USER MENU | ASGER | 4 | 1 |  |  | 0%
PRODUCT CARDS | HELENA | 5 | 4 |  |  | 0%
PRODUCT VIEW | MIKKEL | 5 | 5 |  |  | 0%
PRODUCT SPEC. | MIKKEL | 10 | 4 |  |  | 0%
PRODUCT DESC. | MIKKEL | 14 | 4 |  |  | 0%
COLOR SELECT | MIKKEL | 18 | 3 |  |  | 0%
PURCHASE OPT. | MIKKEL | 21 | 1 |  |  | 0%
ADD. INFO. | MIKKEL | 22 | 4 |  |  | 0%
SIDE NAV | NICKI | 6 | 7 |  |  | 0%
FILTER OPT. | ASGER | 5 | 6 |  |  | 0%
SORT BY | HELENA | 9 | 11 |  |  | 0%
STAGE | NICKI | 13 | 2 |  |  | 0%
SEARCH BAR FUNCTIONAL | ASGER | 11 | 8 |  |  | 0%